## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Feb 27, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-02-27 | 9:00 | 15:00 | 6 | Learning on JavaScript | The project will be developed using React-Flow | Trying to build some tiny project with JS
Tuesday | 2023-02-28 | 18:00 | 23:00 | 5 | Learning on JavaScript, group meeting | The project will be developed using React-Flow | Trying to build some tiny project with JS
Wednesday | 2023-03-01 | 9:00 | 15:00 | 6 | Building some tiny project with JS | The project will be developed using React-Flow | More familiarise with the JS
Thursday | 2023-03-02 | 9:30 | 14:30 | 5 | Building some tiny project with JS, group meeting | The project will be developed using React-Flow | More familiarise with the JS
Friday | 2023-03-03 | 9:00 | 12:00 | 3 | Reading the Literature, client and group meeting | Better understanding of the client's NVAL system
Saturday | 2023-03-04 | 9:00 | 16:00 | 7 | Learning on React, client and group meeting | The project will be developed using React-Flow | Understand some features in React
|  |  | Total | 32

## Sheet2
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Mar 6, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-03-06 | 9:00 | 15:00 | 6 | Learning on React | The project will be developed using React-Flow | Understand some features in React
Tuesday | 2023-03-07 | 18:00 | 23:00 | 5 | Learning on React-Flow, group meeting | The project will be developed using React-Flow | Trying to build a user interface with drag-and-drop in react-flow
Wednesday | 2023-03-08 | 9:00 | 14:00 | 5 | Learning on React-Flow | The project will be developed using React-Flow | Trying to build a user interface with drag-and-drop in react-flow
Thursday | 2023-03-09 | 9:30 | 14:30 | 5 | Build user interface with drag-and-drop properties, slient and group meeting | The user interface can be used as a foundation for the project | Continue working on the user interface
Friday | 2023-03-10 | 9:00 | 12:00 | 3 | Build user interface with drag-and-drop properties | The user interface can be used as a foundation for the project | Continue working on the user interface
Saturday | 2023-03-11 | 9:00 | 16:00 | 7 | Build user interface with drag-and-drop properties, group meeting | The user interface can be used as a foundation for the project | Continue working on the user interface
|  |  | Total | 31

## Sheet3
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Mar 13, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-03-13
Tuesday | 2023-03-14 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-03-15
Thursday | 2023-03-16 | 13:30 | 14:30 | 1 | client and group meeting | project tracking
Friday | 2023-03-17 | 15:00 | 20:00 | 5 | working on the pitch ppt
Saturday | 2023-03-18 | 11:00 | 23:00 | 10 | working on the pitch ppt, group meeting | project assessment, project tracking
|  |  | Total | 17

## Sheet4
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Mar 20, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-03-20
Tuesday | 2023-03-21 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-03-22
Thursday | 2023-03-23 | 13:30 | 18:30 | 3 | client and group meeting, preparing for the pitch and minutes | project tracking, project assessment
Friday | 2023-03-24 | 17:00 | 22:00 | 4 | Pitch preparation and recording | project assessment
Saturday | 2023-03-25 | 15:00 | 23:00 | 8 | group meeting, preparing business case | project tracking, project assessment | continue on business case
|  |  | Total | 16

## Sheet5
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Mar 27, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-03-27
Tuesday | 2023-03-28 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-03-29
Thursday | 2023-03-30 | 9:00 | 23:00 | 14 | Working on the problems for saving key of attributes | Adding attributes on the nodes is one of the feature | Issue solved, then function to save the flow diagram and attribute inputs
Friday | 2023-03-31 | 9:00 | 23:00 | 14 | Developing function to save the diagram and attributes | Saving the attributes as JSON object is one of the target output of the user interface | Able to save diagram but not attributes
Saturday | 2023-04-01 | 9:00 | 23:00 | 14 | Further work on saving the attributes | Saving the attributes as JSON object is one of the target output of the user interface | Issue solved, create function to restore the stored diagram
|  |  | Total | 43

## Sheet6
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Apr 3, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-04-03 | 9:00 | 23:00 | 14 | Further work on restoring the flow diagram | Loading from JSON input is one of the target feature of the interface
Tuesday | 2023-04-04 | 9:00 | 23:00 | 14 | Further work on updating node label, group meeting | Updating node label is important for the graphical design for the user | Can only update the node after clicking the node again, which is not desired. It is highly preferred the node can be updated after clicking the save buttong, further work is needed
Wednesday | 2023-04-05 | 9:00 | 18:00 | 9 | Updating the node label according to the attributes | Updating node label is important for the graphical design for the user | Cannot throw the function to the child JS file as props with different approach, try to explore another approach
Thursday | 2023-04-06 | 13:30 | 14:30 | 1 | client and group meeting | project tracking
Friday | 2023-04-07
Saturday | 2023-04-08 | 20:00 | 21:00 | 1 | group meeting | project tracking
|  |  | Total | 39

## Sheet7
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Apr 17, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-04-17 | 9:00 | 13:00 | 4 | Exploring other approach to update the node label | Updating node label is important for the user interface
Tuesday | 2023-04-18 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-04-19 | 9:00 | 13:00 | 4 | Exploring other approach to update the node label | Updating node label is important for the user interface
Thursday | 2023-04-20 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-04-21 | 9:00 | 17:00 | 8 | Exploring other approach to update the node label | Updating node label is important for the user interface
Saturday | 2023-04-22 | 20:00 | 21:00 | 1 | group meeting | project tracking
|  |  | Total | 19

## Sheet8
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Apr 24, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-04-24 | 9:00 | 15:00 | 6 | Learn how to read all the attributes from the graph | Export the graphical design of the graph as a json file
Tuesday | 2023-04-25 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-04-26 | 9:00 | 13:00 | 4 | Learn how to read all the attributes from the graph | Export the graphical design of the graph as a json file
Thursday | 2023-04-27 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-04-28 | 9:00 | 13:00 | 4 | Learn how to read all the attributes from the graph | Export the graphical design of the graph as a json file
Saturday | 2023-04-29 | 20:00 | 21:00 | 1 | group meeting | project tracking
Sunday | 2023-04-30 | 8:00 | 21:00 | 13 | Learn how to create a json file with the attributes read from the graph | Export the graphical design of the graph as a json file
|  |  | Total | 30

## Sheet9
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | May 1, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-05-01 | 9:00 | 15:00 | 6 | Learn how to create a json file with the attributes read from the graph | Export the graphical design of the graph as a json file
Tuesday | 2023-05-02 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-05-03 | 9:00 | 12:00 | 3 | Learn how to read save attributes | Import the graphical design of the graph from a json file
Thursday | 2023-05-04 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-05-05 | 9:00 | 15:00 | 6 | Learn how to read save attributes | Import the graphical design of the graph from a json file
Saturday | 2023-05-06 | 20:00 | 21:00 | 1 | group meeting | project tracking
Sunday | 2023-05-07 | 8:00 | 21:00 | 13 | Learn how to read save attributes | Import the graphical design of the graph from a json file
|  |  | Total | 31

## Sheet10
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | May 8, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-05-08 | 6:00 | 9:00 | 3 | Learn how to draw graph from the attributes get from the json file | Import the graphical design of the graph from a json file
Tuesday | 2023-05-09 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-05-10 | 6:00 | 9:00 | 3 | Learn how to draw graph from the attributes get from the json file | Import the graphical design of the graph from a json file
Thursday | 2023-05-11 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-05-12 | 6:00 | 8:00 | 2 | Learn how to draw graph from the attributes get from the json file | Import the graphical design of the graph from a json file
Saturday | 2023-05-13 | 15:00 | 21:00 | 6 | Learn how to draw graph from the attributes get from the json file, group meeting | Import the graphical design of the graph from a json file, project tracking
Sunday | 2023-05-14 | 8:00 | 21:00 | 13 | Learn how to draw graph from the attributes get from the json file | Import the graphical design of the graph from a json file
|  |  | Total | 29

## Sheet11
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | May 15, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-05-15 | 6:00 | 12:00 | 6 | Testing the drag-and-drop editor | Testing and debugging for the user interface
Tuesday | 2023-05-16 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-05-17 | 6:00 | 9:00 | 3 | Learn react admin | Create list of graph by using react admin
Thursday | 2023-05-18 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-05-19 | 6:00 | 12:00 | 6 | Learn react admin | Create list of graph by using react admin
Saturday | 2023-05-20 | 20:00 | 21:00 | 1 | group meeting | project tracking
Sunday | 2023-05-21 | 8:00 | 21:00 | 13 | Learn react admin | Create list of graph by using react admin
|  |  | Total | 31

## Sheet12
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | May 22, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-05-22 | 6:00 | 9:00 | 3 | Create list page of current graph design | Create an infrastructure page to display all the avaiable structure
Tuesday | 2023-05-23 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-05-24 | 6:00 | 9:00 | 3 | Create list page of current graph design | Create an infrastructure page to display all the avaiable structure
Thursday | 2023-05-25 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-05-26 | 6:00 | 15:00 | 9 | Create list page of current graph design | Create an infrastructure page to display all the avaiable structure
Saturday | 2023-05-27 | 20:00 | 21:00 | 1 | group meeting | project tracking
Sunday | 2023-05-28 | 8:00 | 21:00 | 13 | Create list page of current graph design | Create an infrastructure page to display all the avaiable structure
|  |  | Total | 31

## Sheet13
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | May 29, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-05-29 | 6:00 | 9:00 | 3 | Testing the infrastructure page | Testing and debugging for the infrastructure page
Tuesday | 2023-05-30 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-05-31 | 6:00 | 12:00 | 6 | Create a temporary experimental page | Create an add function for the experimental page
Thursday | 2023-06-01 | 13:30 | 14:30 | 1 | group meeting | project tracking
Friday | 2023-06-02 | 6:00 | 12:00 | 6 | Create a temporary page for after clicking the add button | Create an add function for the experimental page
Saturday | 2023-06-03 | 20:00 | 21:00 | 1 | group meeting | project tracking
Sunday | 2023-06-04 | 8:00 | 23:00 | 15 | Create an add function | Create an add function for the experimental page
|  |  | Total | 33

## Sheet14
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1865524 |  |  | Week starting: | Jun 6, 2023
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-06-06 | 6:00 | 15:00 | 9 | Create an add function | Create an add function for the experimental page
Tuesday | 2023-06-07 | 20:00 | 21:00 | 1 | group meeting | project tracking
Wednesday | 2023-06-08 | 6:00 | 15:00 | 9 | Create an add function | Create an add function for the experimental page
Thursday | 2023-06-09 | 9:00 | 15:00 | 6 | Create an add function | Create an add function for the experimental page
Friday | 2023-06-10 | 9:00 | 15:00 | 6 | Testing all function | Testing and Debugging
Saturday | 2023-06-11 | 20:00 | 21:00 | 1 | group meeting | project tracking
|  |  | Total | 32