## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-03-13
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-03-13 | 8:00 | 11:00 | 3 | Write codes based on the existing components of reactflow | Write codes according to the project needs | Finish the drag and drop demo
|  | 19:00 | 22:00 | 3
Tuesday | 2023-03-14 | 20:00 | 11:00 | 3
Tuesday | 2023-03-14 | 20:00 | 21:30 | 1.5 | Group meeting | Review the demo and make some modifications | Finish the task of first spring
Wednesday | 2023-03-15 | 8:00 | 11:00 | 3 | Learn some other examples of reactflow, such as update nodes and edges, delete nodes and edges, etc. | These functions are also helpful to design the user interface | Know all codes in these functions and use them
Thursday | 2023-03-16 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show the demo of user interface we designed | The client thinks our demo is good and puts forward other demands: 1. add/delete/save attributes to nodes and edges 2. define 6 types of nodes and use different colour to represent them 3. load json files 4. add and remove nodes and edges
Thursday | 2023-03-16 | 14:30 | 16:00 | 1.5 | Group meeting | Assign tasks to the members | My task is to finish the demand: add/delete/save attributes to nodes and edges
Friday | 2023-03-17 | 20:00 | 23:00 | 3 | Write codes to finish the function: When clicking on the nodes or edges, the new editing page will pop out | Write code according to project plan and requirements | Finish this function by using selected function, node ID and edge ID, and recording the state of the nodes and edges to call the function of the editing page
Saturday | 2023-03-18 | 13:00 | 17:00 | 4
Saturday | 2023-03-18 | 20:00 | 21:30 | 1.5 | Group meeting | Track the progress of tasks completion | Tasks are progressing smoothly
Sunday | 2023-03-19 | 13:00 | 16:00 | 3 | Write codes to finish the function: Add/delete/save attributes of nodes and edges | Add/delete/save attributes of nodes and edges to manage the information of blockchain network according to project plan and requirements | Finish part of code for this function by creating a dialog function containing add/delete/save function
|  |  | Total | 27.5