## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-03-20
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-03-20 | 19:00 | 23:00 | 4 | Write codes to finish the function: Add/delete/save attributes of nodes | Add/delete/save attributes of nodes and edges to manage the information of blockchain network according to project plan and requirements | Finish this function
Tuesday | 2023-03-21 | 8:00 | 11:00 | 3
Tuesday | 2023-03-21 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code and make some modifications | Finish the code
Thursday | 2023-03-23 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show the functions of user interface: 1. add/delete/save attributes to nodes and edges 2. define 6 types of nodes and use different colour to represent them | The client thinks our user interface is good，but these functions have not been merged, this may cause problems to develop an application, and we should develop on a master branch.
Thursday | 2023-03-23 | 14:30 | 16:00 | 1.5 | Group meeting | Assign tasks to the members | My task is to merge my code with others and add a key value of attributes to nodes and edges
Thursday | 2023-03-23 | 20:00 | 22:00 | 2 | Pitch presentation | Make pitch presentation of the project | Finish pitch presentation
Friday | 2023-03-24 | 20:00 | 23:00 | 3 | Merge my code with others' code | Ensuring code integrity to avoid some problems | Finish merging
Saturday | 2023-03-25 | 13:00 | 16:00 | 3 | Write codes to finish the function: When clicking on the nodes or edges, the editing window will pop out on the same page | Improve the functionality of the user interface | Keep modifying code
Saturday | 2023-03-25 | 19:00 | 21:30 | 2.5 | Group meeting | Track the progress of tasks completion Write the business case of the project | 1. Tasks are progressing smoothly 2. Finish the draft of the business case
Sunday | 2023-03-26 | 13:00 | 16:00 | 3 | Write codes to finish the function: When clicking on the nodes or edges, the editing window will pop out on the same page | Improve the functionality of the user interface | Finish this function: in the main App.js, modifying codes in the HTML part code
|  |  | Total | 24.5