## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-03-27
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-03-27 | 19:00 | 22:00 | 3 | Write codes to finish the function: Add a key value for attributes by using dropdown box | Improve the functionality of the user interface | Finish this function, only can select the valuesbut cannot save key value
Tuesday | 2023-03-28 | 9:00 | 12:00 | 3
Tuesday | 2023-03-28 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code and make some modifications | Also cannot save key value
Wednesday | 2023-03-29 | 19:00 | 22:00 | 3 | Search some learning material and ask some friends to fix the problem of saving key value | Try to fix the code problem | Try to fix the code problem
Thursday | 2023-03-30 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show the functions of user interface: 1. When clicking on the nodes or edges, the editing window will pop out on the same page 2. Add a key value for attributes by using dropdown box Show our business case | The client thinks our improvement is good and puts forward some new ideas, such as showing some information on nodes. He gives some suggestion to our business case.
Thursday | 2023-03-30 | 14:30 | 16:00 | 1.5 | Group meeting | Modify the business case Assign tasks to the members | Finish the business case My task is to fix the problem of saving key value
Friday | 2023-03-31 | 20:00 | 23:00 | 3 | Fix the problem of saving key value | Try to fix the code problem | Try to fix the code problem
Saturday | 2023-04-01 | 13:00 | 16:00 | 3 | Fix the problem of saving key value | Try to fix the code problem | Fix the problem
Saturday | 2023-04-01 | 20:00 | 21:30 | 1.5 | Group meeting | Track the progress of tasks completion | Tasks are progressing smoothly
Sunday | 2023-04-02 | 12:00 | 16:00 | 4 | Read the json file from the client | Know the type of attributes of nodes and edges in this project | Familiar with the type of attributes and next step is to update options in the dropdown box of key value
|  |  | Total | 24.5