## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-04-03
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-04-03 | 9:00 | 12:00 | 3 | Write codes to set key options according to the json file | According to the json file used in the project, set key options of node attributes and edge attributes | Finish setting options
Tuesday | 2023-04-04 | 9:00 | 12:00 | 3 | Search a MERN project on Youtube to do practical exercises | MERN project is a full-stack web development framework based on the JavaScript technology stack | Learn MERN project
Tuesday | 2023-04-04 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code | Finish code merge
Wednesday | 2023-04-05 | 9:00 | 12:00 | 3 | Do practical exercises of a MERN project | MERN project is a full-stack web development framework based on the JavaScript technology stack | Learn MERN project
Thursday | 2023-04-06 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show all full functions of user interface | The client thinks our user interface is good and we need to make some small improvements. In next spring,we can move on to the next phase of the project
Thursday | 2023-04-06 | 14:30 | 16:00 | 1.5 | Group meeting | Assign tasks to every member | My task is to set default attributes of nodes and edges.
Friday | 2023-04-07 | 9:00 | 12:00 | 3 | Set default attributes of nodes and edges | When creating new nodes and edges, these default attributes can help to reduce time on modifying attributes | Finish setting default attributes of nodes and edges
Saturday | 2023-04-08 | 13:00 | 16:00 | 3 | Do practical exercises of a MERN project | MERN project is a full-stack web development framework based on the JavaScript technology stack | Learn MERN project
Saturday | 2023-04-08 | 20:00 | 21:30 | 1.5 | Group meeting | Track the progress of tasks completion | Tasks are progressing smoothly
Sunday | 2023-04-09 | 12:00 | 16:00 | 4 | Do practical exercises of a MERN project | MERN project is a full-stack web development framework based on the JavaScript technology stack | Learn MERN project
|  |  | Total | 24.5