## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-05-01
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-05-01 | 8:00 | 12:00 | 4 | Write the code to import a json file | Import node type and attribute options of nodes and edges | Finish the code
Tuesday | 2023-05-02 | 9:00 | 16:00 | 7 | Fix the problem that after importing a json file, the attributes cannot be saved | Import node type and attribute options of nodes and edges by a json file | Fix the problem, some variable names are wrong.
Tuesday | 2023-05-02 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code | Finish code merge
Wednesday | 2023-05-03 | 9:00 | 13:00 | 4 | Finish the json file and code, test the function | Import node type and attribute options of nodes and edges by a json file | Finish the function testing
Thursday | 2023-05-04 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show all full functions of user interface | The client proposed to solve the problem of the code and set connection rules
Thursday | 2023-05-04 | 14:30 | 16:00 | 1.5 | Group meeting | Discuss the final milestone plan | Finish the final milestone plan
Friday | 2023-05-05 | 9:00 | 15:00 | 6 | Set connection rules to prohibit certain nodes from connecting | According to actual needs, some nodes cannot be connected | Write codes for this function
Saturday | 2023-05-06 | 12:00 | 18:00 | 6 | Set connection rules to prohibit certain nodes from connecting | According to actual needs, some nodes cannot be connected | Write codes for this function
|  |  | Total | 31