## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-05-08
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-05-08 | 8:00 | 12:00 | 4 | Set connection rules to prohibit certain nodes from connecting | According to actual needs, some nodes cannot be connected | Set to red and green nodes cannot connect,blue and yellow nodes cannot connect
Tuesday | 2023-05-09 | 12:00 | 17:00 | 5 | Check the hard code problem | The project requirement is that various input information can be changed | Review the code and check all the variables
Tuesday | 2023-05-09 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code and discuss the testing plan
Wednesday | 2023-05-10 | 9:00 | 14:30 | 5.5 | Find all the variables that have the hard code problem | The project requirement is that various input information can be changed | Find all the variables that have the hard code problem
Thursday | 2023-05-11 | 12:30 | 16:00 | 3.5 | Modify the code to solve the hard code problem | The project requirement is that various input information can be changed | Finish the code modification and solve the problem
Friday | 2023-05-12 | 10:00 | 15:00 | 5 | Read the code provided by client about the current platform | This platform is the current one that is designed by the client | Understand the current platform
Saturday | 2023-05-13 | 12:00 | 16:00 | 4 | Read the code provided by client about the current platform | This platform is the current one that is designed by the client | Understand the current platform
Sunday | 2023-05-14 | 20:00 | 22:00 | 2 | Group meeting | Discuss the testing plan | Finish the testing plan
|  |  | Total | 30.5