## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-05-22
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-05-22 | 9:00 | 14:00 | 5 | Learn TypeScript | According to the code provided by the client, all the files are ts files | Learn TypeScript
Tuesday | 2023-05-23 | 9:00 | 14:00 | 5 | Learn TypeScript | According to the code provided by the client, all the files are ts files | Learn TypeScript
Tuesday | 2023-05-23 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code and discuss about the problem of ts files
Wednesday | 2023-05-24 | 12:00 | 17:00 | 5 | Find some methods to merge our js files to these ts files | According to the code provided by the client, all the files are ts files | It is hard to finish the task.
Thursday | 2023-05-25 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show that we add our interface to the platform, but because the current platform uses TypeScript and we use JavaScript, so it is unable to achieve interaction | The client gave us some idea that using react admin to design a new platform.
Thursday | 2023-05-25 | 14:30 | 16:00 | 1.5 | Group meeting | Assign tasks to every member | My task is the function of creating new infrastructures and deleting infrastructures
Friday | 2023-05-26 | 10:00 | 17:00 | 7 | Learn React Admin | React Admin is a a frontend framework for building data-driven applications running in the browser. We need to use the framework to build our platform | Learn React Admin
Saturday | 2023-05-27 | 13:00 | 19:00 | 6 | Learn React Admin | React Admin is a a frontend framework for building data-driven applications running in the browser. We need to use the framework to build our platform | Learn React Admin
Sunday | 2023-05-28 | 12:00 | 14:00 | 2 | Work on the function of creating new infrastructures | Infrastructures are networks generated by the interface we designed to connect different nodes | Write the code of the function
|  |  | Total | 34