## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-05-29
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-05-29 | 9:00 | 14:00 | 5 | Work on the function of creating new infrastructures | Infrastructures are networks generated by the interface we designed to connect different nodes | Write the code of the function
Tuesday | 2023-05-30 | 9:00 | 14:00 | 5 | Work on the function of creating new infrastructures and deleting infrastructures | Infrastructures are networks generated by the interface we designed to connect different nodes | Finish the function of creating new infrastructures and work on deleting infrastructures
Tuesday | 2023-05-30 | 20:00 | 21:30 | 1.5 | Group meeting | Review the code | Merge the code
Wednesday | 2023-05-31 | 9:00 | 15:00 | 6 | Work on the function of deleting infrastructures | Infrastructures are networks generated by the interface we designed to connect different nodes | Finish the function of deleting infrastructures
Thursday | 2023-06-01 | 13:30 | 14:30 | 1 | Weekly meeting with the client | Show the platform we designed | The client suggested that we need more functions, including experiment page, update from the backend, and get result from the NVAL system
Thursday | 2023-06-01 | 14:30 | 16:00 | 1.5 | Group meeting | Assign tasks to every member | My task is to implement the Run function of experiment and update infrastructures
Friday | 2023-06-02 | 9:00 | 15:00 | 6 | Work on the function of updating infrastructure | In the list page of infrastructures, we can modify the contents of infrastructures. | Work on the function of updating infrastructure
Saturday | 2023-06-03 | 10:00 | 15:00 | 5 | Work on the function of updating infrastructure | In the list page of infrastructures, we can modify the contents of infrastructures. | Finish the function
Sunday | 2023-06-04 | 12:00 | 17:00 | 5 | Build interaction between infrasturctures and node graph | In the list page of infrastructures, click "Edit" button, then jump to node graph | Work on the function of interaction between infrasturctures and node graph
|  |  | Total | 36