## Sheet1
MCI Project Weekly Time Sheet
Team | 4 | Student ID | a1829951 |  |  | Week starting: | 2023-06-06
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2023-06-05 | 14:00 | 21:00 | 7 | Build interaction between infrasturctures and node graph | In the list page of infrastructures, click "Edit" button, then jump to node graph | Finish the function
Tuesday | 2023-06-06 | 13:00 | 19:00 | 6 | Work on the Run function of experiments | Send infrastructures to the backend to run experiments | Work on the Run function of experiments
Wednesday | 2023-06-07 | 13:00 | 18:00 | 5 | Work on the Run function of experiments | Send infrastructures to the backend to run experiments | Work on the Run function of experiments
Wednesday | 2023-06-07 | 20:00 | 21:30 | 1.5 | Group meeting | Discuss what the results from backend should be and how to make the poster | Discuss what the results from backend should be and how to make the poster
Thursday | 2023-06-08 | 14:00 | 17:00 | 3 | Work on the Run function of experiments | Send infrastructures to the backend to run experiments | Finish the function
Friday | 2023-06-09 | 14:00 | 17:00 | 5 | Final report | Write the final report of the project | Work on the final report
Friday | 2023-06-09 | 19:00 | 21:00 | 2 | Poster | Used for the presentation | Finish the poster
Saturday | 2023-06-10 | 14:00 | 21:00 | 7 | Final report | Write the final report of the project | Work on the final report
Sunday | 2023-06-11 | 14:00 | 21:00 | 7 | Final report | Write the final report of the project | Finish the final report
|  |  | Total | 43.5