## Sheet2
MCI Project Weekly Time Sheet
Team | 4 | Student ID | 1869462 |  |  | Week starting: | 2023-05-15
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2023-05-15
Tuesday | 2023-05-16 | 16:00 | 19:00 | 3 | Group meeting, working on the node connection rules function | Discuss what to ask the supervisor on Thursday,project function | review，next milestone
Wednesday | 2023-05-17 | 10:00 | 13:00 | 3 | working on the node connection rules function | project function | Achieved the node connection rules function
Thursday | 2023-05-18 | 13:30 | 15:00 | 2 | Group meeting | project tracking | Current progess basically perfect and no need to modify. Next step: merge our interface with the new platform based on the NVAL framework
Saturday | 2023-05-20 | 16:00 | 19:00 | 3 | Checking the new platform | project function | The new platform uses TypeScript, but our interface use JavaScript
Sunday | 2023-05-21 | 20:00 | 21:00 | 1 | Group meeting | project tracking | We have to refactor our code in order to meet the TS code of the new platform
|  |  | Total | 12